## Gant Chart
YOUR COMPANY LOGO HERE
PROJECT TITLE:
|  | Project Start: | 2021-09-27
|  | Display Week: | 0 |  | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25
 | time axis 2021-09-20 to 2021-10-31
TASK | ASSIGNED TO | PROGRESS | START | END | [42 empty] | THREE MONTH GOALS | SIX MONTH GOALS | YEAR 1 GOALS | YEAR 2 GOALS | YEAR 3 GOALS | YEAR 4 GOALS | YEAR 5 GOALS | time axis 2021-09-20 to 2021-10-31
Module 1
Accomodation |  | 50% | 2021-09-20 | 2021-09-23 | [42 empty] | Family in safe accomodation | house buying understood and agents engaged.
Registering with a Doctor |  | 100% | 2021-10-08 | 2021-10-09
Personal bank accounts |  | 50% | 2021-10-10 | 2021-10-12
Join Community |  | 100% | 2021-09-27 | 2021-09-28
Module 2
Business bank account |  | 0% | 2021-10-05 | 2021-10-12 | [42 empty] | home insurance in place | Chidlren settled in School
Choose accountant |  | 20% | 2021-10-06 | 2021-10-16
Registering with Companies house |  | 0% | 2021-10-14 | 2021-10-20
Business cash flow |  | 15% | 2021-10-05 | 2021-10-19
Module 3
Setting your companies goals |  | 40% | 2021-10-03 | 2021-10-22 | [42 empty] | enrolled in school | medical needs met
Target ideal customer |  | 15% | 2021-10-03 | 2021-10-22
Website construction |  | 5% | 2021-10-19 | 2021-11-29
Digital marketing & social media |  | 25% | 2021-10-19 | 2021-11-29
Module 4
Securing funds & finance |  | 0% | 2021-12-01 | 2022-01-17 | [42 empty] | esential direct debits set up e.g bills / council tax | Clear value proposition .
Employing people |  | 0% | 2022-03-14 | 2022-07-15
Intellectual Property |  | 0% | 2021-12-01 | 2021-12-14
Success GPS |  |  | 2022-01-05 | 2022-02-12
Sales Geek |  | 0% | 2022-02-11 | 2022-03-04
Task 5 | [46 empty] | Bank account set up | Brand / logos created
Task 5.1 |  | 0%
Task 6
task 6.1 |  | 0%
Task 7
task 7.1 |  | 0% | [44 empty] | Bank account being used for peronal needs | Website partner / tools identified
Task 8
task 8.1 |  | 0%
Task 9
task 9.1 |  | 0%
Task 10 | [46 empty] | laguage support / course identified and nerolled on | website started
task 10.1 |  | 0%
Task 11
task 11.1 |  | 0%
Task 12
task 12.1 |  | 0% | [44 empty] | Buiness bank account set up | Understadningsocial media and which forms to use
Task 13 | [46 empty] | Buiness map created with 10/ 5 / 3 and 1 year / 9 month/ 6 month / 3 month goals set. .
task 13.1 |  | 0%
Task 14
task 14.1 |  | 0%